## 90-Day Action Plan
AI EXPLAINER CHANNEL — 90-Day Action Plan
Track your progress week by week. Mark Done when completed.
Phase | Week | Task | Category | Priority | Status | Notes
Foundation (Days 1-7) | Week 1 | Create YouTube channel with optimized name & description | Setup | HIGH | To Do | Channel name ideas: AI Simply, Decoded AI, Plain AI
Foundation (Days 1-7) | Week 1 | Design channel art & profile picture in Canva | Branding | HIGH | To Do | Use Canva free template — dark bg + bold channel name
Foundation (Days 1-7) | Week 1 | Create Instagram account matching YouTube brand | Setup | HIGH | To Do | Same username as YouTube if available
Foundation (Days 1-7) | Week 1 | Sign up for affiliate programs (Jasper, Copy.ai, Notion) | Monetization | HIGH | To Do | Get your unique affiliate links before first video
Foundation (Days 1-7) | Week 1 | Research top 10 AI keywords using TubeBuddy (free tier) | SEO | MEDIUM | To Do | Target keywords with high search + low competition
Foundation (Days 1-7) | Week 1 | Script first 3 videos using Claude/ChatGPT | Content | HIGH | To Do | Use prompt: 'Script 7-min explainer on [topic] for non-technical people'
Foundation (Days 1-7) | Week 1 | Record channel trailer (60-90 seconds) | Content | HIGH | To Do | Hook: 'If AI feels overwhelming, this channel is for you'
Foundation (Days 1-7) | Week 1 | Set up free ConvertKit/Beehiiv account for email list | Setup | MEDIUM | To Do | Start building email list from day 1
Launch (Days 8-30) | Week 2 | Publish Video 1: 'How ChatGPT Actually Works (Simply Explained)' | Content | HIGH | To Do | Aim for 8-10 min. Add timestamps, SEO description, affiliate links
Launch (Days 8-30) | Week 2 | Create Instagram Reel from Video 1 highlight (60-90 sec) | Content | HIGH | To Do | Hook in first 3 seconds. Add captions. Post same day as YT upload
Launch (Days 8-30) | Week 2 | Design Video 1 thumbnail in Canva | Content | HIGH | To Do | Formula: your face + surprised expression + bold 2-3 word text
Launch (Days 8-30) | Week 2 | Comment on 10 videos in your niche to build visibility | Growth | MEDIUM | To Do | Add genuine value. Never spam. Builds community visibility
Launch (Days 8-30) | Week 3 | Publish Video 2: 'I Used AI for Everything for 7 Days' | Content | HIGH | To Do | Tutorial format works very well. Include screen recordings
Launch (Days 8-30) | Week 3 | Create Instagram carousel: '5 AI Tools You Should Try' | Content | MEDIUM | To Do | Carousels get 3x more reach than static posts on IG
Launch (Days 8-30) | Week 3 | Set up Gumroad account and create first digital product | Monetization | MEDIUM | To Do | 'The 50 Best ChatGPT Prompts for Beginners' — sell for $9
Launch (Days 8-30) | Week 4 | Publish Video 3: 'What is Machine Learning? (With Examples)' | Content | HIGH | To Do | Concept explainer. Use analogies. Animated visuals if possible
Launch (Days 8-30) | Week 4 | Analyze Month 1 analytics — what performed best? | Analytics | HIGH | To Do | Focus: watch time %, click-through rate, top search terms
Launch (Days 8-30) | Week 4 | Write Month 1 newsletter issue (repurpose video script) | Content | LOW | To Do | Substack or Beehiiv. Short + helpful. Link to your latest video
Momentum (Days 31-60) | Week 5 | Publish Video 4: 'The AI Tool That Changed How I Work' | Content | HIGH | To Do | Tool deep dive. Compare 2-3 tools. Include affiliate links
Momentum (Days 31-60) | Week 5 | Set up Repurpose.io for auto-distribution | Automation | HIGH | To Do | Connect YouTube → Instagram + TikTok auto-posting
Momentum (Days 31-60) | Week 6 | Publish Video 5: 'What is Generative AI? (Easy Explanation)' | Content | HIGH | To Do | High search volume topic. Great for new subscriber traffic
Momentum (Days 31-60) | Week 6 | Reach out to 3 small AI companies about micro-sponsorships | Monetization | MEDIUM | To Do | Email template: introduce yourself, share channel stats + audience
Momentum (Days 31-60) | Week 7 | Publish Video 6: 'How AI is Changing [Industry]' | Content | HIGH | To Do | Impact story format. Human angle. Great for shares
Momentum (Days 31-60) | Week 7 | Create second digital product based on audience comments | Monetization | MEDIUM | To Do | What are people asking in your comments? Build a product for that
Momentum (Days 31-60) | Week 8 | Publish Video 7: YouTube Shorts test — repurpose best moment | Content | MEDIUM | To Do | 3-5 Shorts/week can dramatically accelerate subscriber growth
Scale (Days 61-90) | Week 9-10 | Publish 2 videos per week consistently | Content | HIGH | To Do | Consistency is the #1 growth factor. Don't break the streak
Scale (Days 61-90) | Week 9-10 | Target 500 subscribers milestone | Growth | HIGH | To Do | 500 subs → you can have brand deal conversations
Scale (Days 61-90) | Week 11-12 | Review analytics and double down on best content format | Analytics | HIGH | To Do | Which pillar has the highest watch time? Make more of that
Scale (Days 61-90) | Week 11-12 | Start building toward 1,000 subs + 4,000 watch hours | Growth | HIGH | To Do | YT Partner Program milestone — keep this as your 6-month goal
Scale (Days 61-90) | Week 11-12 | Refresh SEO on top 3 videos — update descriptions and tags | SEO | MEDIUM | To Do | Old videos can get new traffic with updated optimization

## Content Calendar
CONTENT CALENDAR — Video Ideas & SEO Keyword Tracker
Use this to plan your first 20 videos. Score = estimated opportunity (1-10). Sort by Score to prioritize.
# | Video Title Idea | Pillar | Target Keyword | Est. Monthly Searches | Competition | Opportunity Score | Status
1 | How ChatGPT Actually Works (Simple Explanation) | Concept | how does chatgpt work | 90K+ | MEDIUM | 9 | Script Ready
2 | What is Machine Learning? (With Everyday Examples) | Concept | what is machine learning explained | 74K+ | MEDIUM | 9 | To Script
3 | I Used AI for Everything for 7 Days — Here's What Happened | Tool | using ai tools for a week | 40K+ | LOW | 9 | To Script
4 | What is a Neural Network? (Animated Explanation) | Concept | neural network explained simply | 60K+ | MEDIUM | 8 | To Script
5 | The Best Free AI Tools of 2026 (Ranked) | Tool | best free ai tools 2026 | 50K+ | LOW | 9 | To Script
6 | GPT vs Gemini vs Claude — Which AI is Actually Better? | Tool | chatgpt vs gemini vs claude | 80K+ | HIGH | 7 | To Script
7 | How AI Actually Learns: Training Explained Simply | Concept | how does ai learn | 55K+ | LOW | 9 | To Script
8 | Midjourney for Complete Beginners (Make AI Images Now) | Tool | midjourney beginner tutorial | 45K+ | MEDIUM | 8 | To Script
9 | How AI is Changing Healthcare (What Doctors Are Saying) | Impact | ai in healthcare explained | 35K+ | LOW | 9 | To Script
10 | What is Generative AI? (The Simple Version) | Concept | generative ai explained simply | 65K+ | LOW | 9 | To Script
11 | Perplexity AI vs Google — Why I Switched | Tool | perplexity ai vs google | 30K+ | LOW | 9 | To Script
12 | How AI Writes Text — What's Actually Happening? | Concept | how does ai generate text | 40K+ | LOW | 8 | To Script
13 | The AI Tools Teachers Are Using Right Now | Impact | ai tools for teachers | 25K+ | LOW | 9 | To Script
14 | What is Prompt Engineering? (And Why It Matters) | Concept | what is prompt engineering | 55K+ | MEDIUM | 8 | To Script
15 | AI That Actually Saves Time: My Honest Workflow | Tool | ai productivity tools 2026 | 30K+ | LOW | 8 | To Script
16 | How Stable Diffusion Works (No PhD Required) | Concept | how does stable diffusion work | 28K+ | LOW | 8 | To Script
17 | AI is Changing These 5 Jobs Forever | Impact | how ai is changing jobs | 70K+ | MEDIUM | 7 | To Script
18 | What is the Difference Between AI and ML? | Concept | ai vs machine learning difference | 45K+ | LOW | 9 | To Script
19 | I Built an AI Chatbot With No Coding — Here's How | Tool | build ai chatbot no code | 35K+ | LOW | 9 | To Script
20 | The Future of AI: What's Actually Coming Next? | Concept | future of ai explained | 60K+ | MEDIUM | 7 | To Script

## Monetization Tracker
MONETIZATION TRACKER — Monthly Income Overview
AFFILIATE PROGRAMS
Program | Commission Rate | Payout Model | Your Link Status | This Month Clicks | This Month Earnings ($)
Jasper AI | 30% recurring | Monthly | Not signed up | 0 | 0
Copy.ai | 45% first year | Monthly | Not signed up | 0 | 0
Descript | 15% recurring | Monthly | Not signed up | 0 | 0
Notion | $10/Pro user | Per sale | Not signed up | 0 | 0
ConvertKit | 30% recurring | Monthly | Not signed up | 0 | 0
Midjourney | Varies | Per referral | Not signed up | 0 | 0
TOTAL AFFILIATE EARNINGS
DIGITAL PRODUCTS
Product Name | Platform | Price ($) | Units Sold | Revenue ($) | Status
AI Prompt Pack for Beginners (50 prompts) | Gumroad | 9 | 0 |  | Not Created
AI Productivity Notion Template | Gumroad | 19 | 0 |  | Not Created
AI Starter Guide PDF | Gumroad | 7 | 0 |  | Not Created
MONTHLY INCOME SUMMARY
Month | Affiliate ($) | Products ($) | Sponsorships ($) | YouTube Ads ($) | Total ($)
Month 1 | 0 | 0 | 0 | 0
Month 2 | 0 | 0 | 0 | 0
Month 3 | 0 | 0 | 0 | 0
Month 4 | 0 | 0 | 0 | 0
Month 5 | 0 | 0 | 0 | 0
Month 6 | 0 | 0 | 0 | 0

## Analytics Dashboard
CHANNEL ANALYTICS DASHBOARD — Weekly Tracker
Fill this in every Sunday. Track the metrics that actually matter for growth.
Week | Date | Subscribers | Sub Growth | Total Views | Watch Hours | Top Video | CTR %
Week 1
Week 2
Week 3
Week 4
Week 5
Week 6
Week 7
Week 8
Week 9
Week 10
Week 11
Week 12
KEY MILESTONES
Milestone | Why It Matters | Status
100 Subscribers | First milestone — don't stop! | In Progress
500 Subscribers | Brand deal conversations begin | Not Started
1,000 Subscribers | YT Partner Program eligible | Not Started
4,000 Watch Hours | YT Partner Program eligible | Not Started
First Affiliate Sale | Monetization officially started | Not Started
First Digital Product Sale | Passive income activated | Not Started
First Sponsorship | You're a professional creator | Not Started
10,000 Subscribers | Significant income unlock | Not Started